## Tasks Description
Rubric | deployment.md
Resources:
Text + Images + Medias |  |  | Rubric + Trello for restrictions
Goal-Driven |  |  | https://wpengine.com/resources/what-is-a-staging-site-why-have-one/
Audience-Driven |  |  | https://github.com/cp3402-students/Coursework_3402_group4/blob/main/deployment.md
Call-To-Action |  |  | https://github.com/cp3402-students/CMS-SP52-2022-Group-2/blob/main/deployment.md
Information Architecture |  |  | Practical Week 4
Navigation |  | Description:
1-2 individuals look through the resources and write the first edition
Then the rest add on their thoughts
deployment.md |  |  | Keep updating it to GitHub for every changes
theme.md | theme.md
Resources:
Theme |  |  | Rubric + Trello for restrictions
site.md |  |  | https://github.com/cp3402-students/Coursework_3402_group4/blob/main/theme.md
Publishing |  |  | https://github.com/cp3402-students/CMS-SP52-2022-Group-2/blob/main/theme.md
Build Site |  |  | Practical Week 5
README.md |  | Description:
LinkedIn Report |  |  | 1-2 individuals look through the rubric and resources and guide the rest to write it together
a2.HTML |  |  | Keep updating it to GitHub for every changes
Presentation | Theme
Resources:
|  |  | Block Design | https://www.youtube.com/watch?v=C088o0O7Snc
https://www.youtube.com/watch?v=-h7gOJbIpmo
Practical Week 5
Practical Week 8
Past Student Website
Others' Theme from the Internet
|  |  | Sample | https://www.thelearninglab.com.sg/programme/preschool/
Description:
Individual design and update to GitHub according to the theme.md
May change theme.md during the process
The team may divide the tasks such that one person will be in charge of one page…
Keep updating it to GitHub for every changes
site.md
Resources:
Rubric + Trello for restrictions
https://github.com/cp3402-students/Coursework_3402_group4/blob/main/site.md
https://github.com/cp3402-students/CMS-SP52-2022-Group-2/blob/main/site.md
Description:
1-2 individuals look through the rubric and resources and guide the rest to write it together
Keep updating it to GitHub for every changes
Publishing
Resources:
|  |  | Staging |  | https://www.youtube.com/watch?v=d0VYbwSmMns
Description:
Create a production site
Create a staging site
One person in charge of
Build Site
a2.HTML
README.md
LinkedIn Report
Peer Evaluation
Presentation

## Gantt Chart
| Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu
| 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-04-30 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11
deployment.md | bar: 2023-04-25 to 2023-04-27
theme.md | bar: 2023-04-25 to 2023-04-27
Theme | bar: 2023-04-27 to 2023-04-30
site.md | bar: 2023-04-30 to 2023-05-01
Publishing | bar: 2023-05-01
Build Site | bar: 2023-05-01 to 2023-05-05
README.md | bar: 2023-05-05
LinkedIn Report | bar: 2023-05-06 to 2023-05-07
a2.HTML | bar: 2023-05-07
Presentation | bar: 2023-05-08 to 2023-05-10
One person in charge
Submission
Four .md files
Required
Due Date

## Design Info
Site: learning center "BaizonnLearningCenter"
specialize in Math and Science from Primary to Junior College
Goals: Increase students' enrolment
Target Audience: Parents + high-school studnets.
NOTE
WordPress posts:
Current sessions
Promotions
Staff details
etc. (events)
Dynamic
WordPress pages:
About us…
Static - not change frequently, not author, data, tag…
Event:
Name: Open House for 2023 Intake
Date: 23rd December 2022, Friday 3pm to 9pm.
Description:
Bookings are essential. Could I please suggest that you make your booking as soon as possible so that you will not be disappointed?
Please contact us on the Center’s email or BaizonnLearning@gmail.com
Or Phone Lum on +65 62811816
Christmas buffet dinner will be arranged for all guests. Vegetarian menu is available too. Kindly indicate your preference during booking.
Unique Baizonn T-Shirt will be given free for all confirmed students during the Open House.
Contatct Details:
Address: 1007A Upper Serangoon Road
General Inquiries: 62811816, or BaizonnLearning@gmail.com
Home Tab:
Welcome to BAIZONN
Founded in 2018, we believe in Establishing a Strong Foundation build on Grasping Maths and Science Principles.
At Baizonn, we Equip your child to ace the semester. We provide up-to-date curriculum and targeted lesson to set your child up for success in the coming terms.
F.A.S.T. = Firm Foundation, Apply, Surpass, Top
S.T.E.M : Science, Technology, Engineering, Maths
About Us Tab:
A center image -- Named: Centre Logo 9
Nurturing a Love For Learning
For over 5 years, we help students achieve success in school and in life by nurturing a love for learning.
From primary school to junior college, our students enjoy fun, interactive and relevant lessons and are empowered to think beyond the confines of the classroom.
Preparing Students To Achieve Success
Developing Confident and Successful Learners
Our students are at the centre of everything we do and their well-being and success in learning matter to us.
While we educate our students, we also equip them with the right knowledge, skills and attitudes that help them solve problems, think big and seek excellence.
Passionate Teachers That Make A Difference
Our teachers motivate and nurture every student to achieve their best and to build the right attitudes to ingrain a love for learning.
We hire teachers with the right passion and qualifications, and equip them to create amazing classroom experiences for their students.
We're committed to bringing out the best in every student.
Registration Tab:
Join Us at Baizonn!
And a contact form
Name*
Contact Number*
Email*
Your school
Your grade
Class interested
Message
Schedule Tab:
Filter -- All classes
A timetable like the one in student first
Other Resources:
Subjects offer
Science
|  | Primary 3-6 | Science | Primary Science
|  | Secondary 1-2 | Science | Secondary 1-2 Science
|  | Secondary 3-4 | Science | Secondary 3-4 Physics, Chemistry and Biology
|  | Junior College 1-2 | Science | Junior College H1, H2 Physics, Chemistry and Biology
Mathematics
|  | Primary 3-6 | Mathematics | Primary Mathematics
|  | Secondary 1-2 | Mathematics | Seconday 1-2 Mathematics
|  | Secondary 3-4 | Mathematics | Seconday 3-4 Elementary Mathematics, Additional Mathematics
|  | Junior College 1-2 | Mathematics | Junior College H1, H2, H3 Mathematics
Advanced Courses
Integrated Programme (IP) Mathematics and Science
International Baccalaureate (IB) Mathematics and Science
Academic Partner
NATIONAL INSTRUMENTS -- we have its logo
Academic Channel Partner for S.T.E.M.
Awards
Winner of Editor’s Choice Awards for 2016 Engineering Impact Awards ASEAN / ANZ Regional Contest
“A Smart Recirculating Aquaculture System”
Total Four awards images -- see the content given
Current Session for 2022
Include the time and monthly fee
View the A01 Center Info word document or the image in Discord
Promotions
For students that enrolled into 2 subjects, there will be 5% discount on the monthly fees.
For students that enrolled into 3 subjects, there will be 10% discount on the monthly fees
Video
Basics Algebra for Beginners
38 mins
https://www.youtube.com/watch?v=PVoTRu3p6ug
12 mins
https://www.youtube.com/watch?v=kWOTmyoaWJg